## Tests Result
Sensor under test | Garmin LIDAR Lite v4 | Progression
Operator | Vincent Savioz | 12.5%
Test ID | S000
Test Description | Wire the sensor, power it on and take distance measurements in a room without sunlight.
Test Prescription | Wire the sensor to the controller (uC, PC, Arduino, etc.) and write a small program that can take distance measurements. The sensor needs to be in a room without any trace of infrared light (i.e. sunlight). Output the measures on a prompt if possible. In order to compare sensors, measures need to be logged.
Expected Result | The sensor take distance measures up to its theorical limit without any problem and show them on the prompt.
Results | After a quick test on Arduino, a programm was developped on a STM32F746G-DISCO board in order to use a more powerful processor. The sensor outputs distance measurments without any problem.
Conclusion | The sensor is working properly according to this test. | Success
Test ID | S001
Test Description | Characterize the distance measurement error of the sensor.
Test Prescription | Fix the sensor on a surface and place an object in front of it at a known distance. Then, note the output distance versus the real distance and characterize its measurement error (proportional, linear, etc.). Create a way of calibrating it if necessary.
Expected Result | After calibration or compensation, the sensor should measure the right distance according to its accuracy
Results
Conclusion |  | Not done
Test ID | S002
Test Description | Optimize measurement results by eliminating value that are too far from the standard deviation.
Test Prescription | Make a program that compute mean and standard deviation from a running or static set of measures. It then deletes extreme values and recompute mean value. It should increase sensor accuracy.
Expected Result | The sensor shouldn't be sensitive to small perturbation in front of it.
Results
Conclusion |  | Not done
Test ID | S003
Test Description | Measure the sensor robustness in the lab sandbox using artificial snow (confettis).
Test Prescription | Fix the sensor on the tripod and make sure it won't move (meaure repeatability). Then, note the sensor angle and floor from the plane and give them to the program in order to calibrate measurements.
Expected Result | The sensor should be able to measure an offset at least 10mm high on the ground, even with perturbations.
Results
Conclusion |  | Not done
Test ID | S004
Test Description | Measure the sensor capability to output a right offset measurement in various temperatures and environnements.
Test Prescription | Take measurements at various temperatures and humidity values, i.e. room temperature, oudoor near-zero temperature, etc. but always without direct sunlight (in a low infrared environment), if possible during the night.
Expected Result | Sensor measurements shouldn't be affected by temperature too much.
Results
Conclusion |  | Not done
Test ID | S005
Test Description | Measure the sensor capability to output a right offset measurement in an overcast outdoor situation (medium infrared environment).
Test Prescription | Take measurements during an overcast day without any direct sunlight.
Expected Result | Sensor measurements shouldn't be too much affected by a medium infrared environment.
Results
Conclusion |  | Not done
Test ID | S006
Test Description | Measure the sensor capability to output a right offset measurement in an sunny outdoor situation (high to very high infrared environment).
Test Prescription | Take measurements during a sunny day in direct sunlight.
Expected Result | Sensor measurements shouldn't be too much affected by a high to very high infrared environment.
Results
Conclusion |  | Not done
Test ID | S007
Test Description | Finally, test the sensor in real snowy condition, at night if necessary.
Test Prescription | Take the sensor outside during a snowy weather, especially in poor visibility conditions in order to take measurements on real snow. Try to measure offsets and log data.
Expected Result | The sensor should be able to measure offset in real conditions.
Results
Conclusion |  | Not done

## Misc
Success
In progress
Failed
Not done